## MMA301_Assignment1_Plan
ID | Phase | Day | Task | Subtask | Requirement / Rubric liên quan | Screen / File / Component liên quan | Input | Expected Output | Evidence cần lưu | Test cần thực hiện | Interview cần biết | AI có thể hỗ trợ gì | AI Verification | Priority | Estimated Time | Status | Notes | COLOR LEGEND
P1-01 | Phase 1 – Requirement Analysis | Day 1 | Read PDF end-to-end | Break requirement into a concrete decision/output. | R01–R10; Rubric 1–2 | Requirements / RTM | Assignment PDF + project | Requirement decisions recorded | Notes + RTM draft | Verify against PDF | Requirement → evidence mapping | Checklist/gap scan | Compare with PDF | HIGH | 30 | DONE |  | PHASE 1 – UNDERSTAND
P1-02 | Phase 1 – Requirement Analysis | Day 1 | Extract scope, screens, workflow, technical constraints and evidence requirements. | Break requirement into a concrete decision/output. | R01–R10; Rubric 1–2 | Requirements / RTM | Assignment PDF + project | Requirement decisions recorded | Notes + RTM draft | Verify against PDF | Requirement → evidence mapping | Checklist/gap scan | Compare with PDF | HIGH | 30 | DONE |  | PHASE 2 – DESIGN
P1-03 | Phase 1 – Requirement Analysis | Day 1 | List screens/navigation | Break requirement into a concrete decision/output. | R01–R10; Rubric 1–2 | Requirements / RTM | Assignment PDF + project | Requirement decisions recorded | Notes + RTM draft | Verify against PDF | Requirement → evidence mapping | Checklist/gap scan | Compare with PDF | HIGH | 30 | DONE |  | PHASE 3 – IMPLEMENT
P1-04 | Phase 1 – Requirement Analysis | Day 1 | Home, Profile, Edit Profile, Activity/Interests, Settings and navigation flow. | Break requirement into a concrete decision/output. | R01–R10; Rubric 1–2 | Requirements / RTM | Assignment PDF + project | Requirement decisions recorded | Notes + RTM draft | Verify against PDF | Requirement → evidence mapping | Checklist/gap scan | Compare with PDF | HIGH | 30 | DONE |  | PHASE 4 – TEST
P1-05 | Phase 1 – Requirement Analysis | Day 1 | Classify state ownership | Break requirement into a concrete decision/output. | R01–R10; Rubric 1–2 | Requirements / RTM | Assignment PDF + project | Requirement decisions recorded | Notes + RTM draft | Verify against PDF | Requirement → evidence mapping | Checklist/gap scan | Compare with PDF | HIGH | 30 | DONE |  | PHASE 5 – REVIEW / COMPLETE
P1-06 | Phase 1 – Requirement Analysis | Day 1 | Mark local UI, shared state, persistent state and hydration. | Break requirement into a concrete decision/output. | R01–R10; Rubric 1–2 | Requirements / RTM | Assignment PDF + project | Requirement decisions recorded | Notes + RTM draft | Verify against PDF | Requirement → evidence mapping | Checklist/gap scan | Compare with PDF | HIGH | 30 | DONE |  | TODO / NOT STARTED
P1-07 | Phase 1 – Requirement Analysis | Day 1 | Define Profile model/validation | Break requirement into a concrete decision/output. | R01–R10; Rubric 1–2 | Requirements / RTM | Assignment PDF + project | Requirement decisions recorded | Notes + RTM draft | Verify against PDF | Requirement → evidence mapping | Checklist/gap scan | Compare with PDF | HIGH | 30 | DONE |  | IN PROGRESS
P1-08 | Phase 1 – Requirement Analysis | Day 1 | Name/avatar/bio, validation, invalid data must not save. | Break requirement into a concrete decision/output. | R01–R10; Rubric 1–2 | Requirements / RTM | Assignment PDF + project | Requirement decisions recorded | Notes + RTM draft | Verify against PDF | Requirement → evidence mapping | Checklist/gap scan | Compare with PDF | HIGH | 30 | DONE |  | BLOCKED
P1-09 | Phase 1 – Requirement Analysis | Day 1 | Define list behavior | Break requirement into a concrete decision/output. | R01–R10; Rubric 1–2 | Requirements / RTM | Assignment PDF + project | Requirement decisions recorded | Notes + RTM draft | Verify against PDF | Requirement → evidence mapping | Checklist/gap scan | Compare with PDF | HIGH | 30 | DONE |  | DONE
P1-10 | Phase 1 – Requirement Analysis | Day 1 | Collection shape, stable key, empty state and state-changing interaction. | Break requirement into a concrete decision/output. | R01–R10; Rubric 1–2 | Requirements / RTM | Assignment PDF + project | Requirement decisions recorded | Notes + RTM draft | Verify against PDF | Requirement → evidence mapping | Checklist/gap scan | Compare with PDF | HIGH | 30 | DONE |  | LOW
P1-11 | Phase 1 – Requirement Analysis | Day 1 | Define persistence behavior | Break requirement into a concrete decision/output. | R01–R10; Rubric 1–2 | Requirements / RTM | Assignment PDF + project | Requirement decisions recorded | Notes + RTM draft | Verify against PDF | Requirement → evidence mapping | Checklist/gap scan | Compare with PDF | HIGH | 30 | DONE |  | MEDIUM
P1-12 | Phase 1 – Requirement Analysis | Day 1 | AsyncStorage keys, JSON serialization, first-run defaults, missing/corrupt fallback. | Break requirement into a concrete decision/output. | R01–R10; Rubric 1–2 | Requirements / RTM | Assignment PDF + project | Requirement decisions recorded | Notes + RTM draft | Verify against PDF | Requirement → evidence mapping | Checklist/gap scan | Compare with PDF | HIGH | 30 | DONE |  | HIGH
P1-13 | Phase 1 – Requirement Analysis | Day 1 | Define theme behavior | Break requirement into a concrete decision/output. | R01–R10; Rubric 1–2 | Requirements / RTM | Assignment PDF + project | Requirement decisions recorded | Notes + RTM draft | Verify against PDF | Requirement → evidence mapping | Checklist/gap scan | Compare with PDF | HIGH | 30 | DONE
P1-14 | Phase 1 – Requirement Analysis | Day 1 | Context placement, app-wide update, hydration and persistence. | Break requirement into a concrete decision/output. | R01–R10; Rubric 1–2 | Requirements / RTM | Assignment PDF + project | Requirement decisions recorded | Notes + RTM draft | Verify against PDF | Requirement → evidence mapping | Checklist/gap scan | Compare with PDF | HIGH | 30 | DONE
P1-15 | Phase 1 – Requirement Analysis | Day 1 | Map end-to-end workflow | Break requirement into a concrete decision/output. | R01–R10; Rubric 1–2 | Requirements / RTM | Assignment PDF + project | Requirement decisions recorded | Notes + RTM draft | Verify against PDF | Requirement → evidence mapping | Checklist/gap scan | Compare with PDF | HIGH | 30 | DONE
P1-16 | Phase 1 – Requirement Analysis | Day 1 | Startup → Profile → Edit → Save → Activity → Settings → restart. | Break requirement into a concrete decision/output. | R01–R10; Rubric 1–2 | Requirements / RTM | Assignment PDF + project | Requirement decisions recorded | Notes + RTM draft | Verify against PDF | Requirement → evidence mapping | Checklist/gap scan | Compare with PDF | HIGH | 30 | DONE
P1-17 | Phase 1 – Requirement Analysis | Day 1 | Identify edge/failure cases | Break requirement into a concrete decision/output. | R01–R10; Rubric 1–2 | Requirements / RTM | Assignment PDF + project | Requirement decisions recorded | Notes + RTM draft | Verify against PDF | Requirement → evidence mapping | Checklist/gap scan | Compare with PDF | HIGH | 30 | DONE
P1-18 | Phase 1 – Requirement Analysis | Day 1 | Invalid form, empty list, missing/corrupt storage, failed async operation. | Break requirement into a concrete decision/output. | R01–R10; Rubric 1–2 | Requirements / RTM | Assignment PDF + project | Requirement decisions recorded | Notes + RTM draft | Verify against PDF | Requirement → evidence mapping | Checklist/gap scan | Compare with PDF | HIGH | 30 | DONE
P1-19 | Phase 1 – Requirement Analysis | Day 1 | Create state/data sketch | Break requirement into a concrete decision/output. | R01–R10; Rubric 1–2 | Requirements / RTM | Assignment PDF + project | Requirement decisions recorded | Notes + RTM draft | Verify against PDF | Requirement → evidence mapping | Checklist/gap scan | Compare with PDF | HIGH | 30 | DONE
P1-20 | Phase 1 – Requirement Analysis | Day 1 | Screen/component/state/data/service relationships. | Break requirement into a concrete decision/output. | R01–R10; Rubric 1–2 | Requirements / RTM | Assignment PDF + project | Requirement decisions recorded | Notes + RTM draft | Verify against PDF | Requirement → evidence mapping | Checklist/gap scan | Compare with PDF | HIGH | 30 | DONE
P1-21 | Phase 1 – Requirement Analysis | Day 1 | Build initial RTM | Break requirement into a concrete decision/output. | R01–R10; Rubric 1–2 | Requirements / RTM | Assignment PDF + project | Requirement decisions recorded | Notes + RTM draft | Verify against PDF | Requirement → evidence mapping | Checklist/gap scan | Compare with PDF | HIGH | 30 | DONE
P1-22 | Phase 1 – Requirement Analysis | Day 1 | Map R01–R10 to implementation, tests, evidence, demo and interview. | Break requirement into a concrete decision/output. | R01–R10; Rubric 1–2 | Requirements / RTM | Assignment PDF + project | Requirement decisions recorded | Notes + RTM draft | Verify against PDF | Requirement → evidence mapping | Checklist/gap scan | Compare with PDF | HIGH | 30 | DONE
P2-01 | Phase 2 – Design | Day 2 | Navigation architecture | Define central navigation and screen responsibilities. | R02–R10; Rubric 2 | Navigation / Context / Components / Storage | Requirement analysis + state sketch | Design ready | Diagram/notes + DDD | Walk through design | Explain why state belongs where | Keep only verified decisions | HIGH | 30 | TODO | DONE
P2-02 | Phase 2 – Design | Day 2 | Screen/component structure | Create component tree for Home, Profile, Edit Profile, Activity, Settings. | R02–R10; Rubric 2 | Navigation / Context / Components / Storage | Requirement analysis + state sketch | Design ready | Diagram/notes + DDD | Walk through design | Explain why state belongs where | Keep only verified decisions | HIGH | 30 | TODO | DONE
P2-03 | Phase 2 – Design | Day 2 | State ownership design | Decide local vs shared state with explicit ownership. | R02–R10; Rubric 2 | Navigation / Context / Components / Storage | Requirement analysis + state sketch | Design ready | Diagram/notes + DDD | Walk through design | Explain why state belongs where | Keep only verified decisions | HIGH | 30 | TODO | DONE
P2-04 | Phase 2 – Design | Day 2 | ThemeContext design | Define provider value, toggle/update and re-render expectations. | R02–R10; Rubric 2 | Navigation / Context / Components / Storage | Requirement analysis + state sketch | Design ready | Diagram/notes + DDD | Walk through design | Explain why state belongs where | Keep only verified decisions | HIGH | 30 | TODO | DONE
P2-05 | Phase 2 – Design | Day 2 | Profile state design | Define shared profile state and immediate UI update after save. | R02–R10; Rubric 2 | Navigation / Context / Components / Storage | Requirement analysis + state sketch | Design ready | Diagram/notes + DDD | Walk through design | Explain why state belongs where | Keep only verified decisions | HIGH | 30 | TODO | DONE
P2-06 | Phase 2 – Design | Day 2 | Persistence architecture | Define AsyncStorage helper, keys, serialization and hydration. | R02–R10; Rubric 2 | Navigation / Context / Components / Storage | Requirement analysis + state sketch | Design ready | Diagram/notes + DDD | Walk through design | Explain why state belongs where | Keep only verified decisions | HIGH | 30 | TODO | DONE
P2-07 | Phase 2 – Design | Day 2 | Hydration timing | Startup loading/default strategy and corrupt-data fallback. | R02–R10; Rubric 2 | Navigation / Context / Components / Storage | Requirement analysis + state sketch | Design ready | Diagram/notes + DDD | Walk through design | Explain why state belongs where | Keep only verified decisions | HIGH | 30 | TODO | DONE
P2-08 | Phase 2 – Design | Day 2 | List design | FlatList/SectionList data, renderItem, keyExtractor and empty state. | R02–R10; Rubric 2 | Navigation / Context / Components / Storage | Requirement analysis + state sketch | Design ready | Diagram/notes + DDD | Walk through design | Explain why state belongs where | Keep only verified decisions | HIGH | 30 | TODO | DONE
P2-09 | Phase 2 – Design | Day 2 | Reusable components | Identify reusable buttons, inputs, cards and list items. | R02–R10; Rubric 2 | Navigation / Context / Components / Storage | Requirement analysis + state sketch | Design ready | Diagram/notes + DDD | Walk through design | Explain why state belongs where | Keep only verified decisions | HIGH | 30 | TODO | DONE
P2-10 | Phase 2 – Design | Day 2 | Validation/error design | Validation rules, errors, save/cancel and failure paths. | R02–R10; Rubric 2 | Navigation / Context / Components / Storage | Requirement analysis + state sketch | Design ready | Diagram/notes + DDD | Walk through design | Explain why state belongs where | Keep only verified decisions | HIGH | 30 | TODO | DONE
P2-11 | Phase 2 – Design | Day 2 | Folder structure | Screens / Components / Context / Services(or utils) organization. | R02–R10; Rubric 2 | Navigation / Context / Components / Storage | Requirement analysis + state sketch | Design ready | Diagram/notes + DDD | Walk through design | Explain why state belongs where | Keep only verified decisions | HIGH | 30 | TODO | DONE
P2-12 | Phase 2 – Design | Day 2 | Design Decision Record | At least 5 decisions with alternatives, trade-offs and change impact. | R02–R10; Rubric 2 | Navigation / Context / Components / Storage | Requirement analysis + state sketch | Design ready | Diagram/notes + DDD | Walk through design | Explain why state belongs where | Keep only verified decisions | HIGH | 30 | TODO | DONE
P3-01 | Phase 3 – Build (M1–M7) | Day 3–6 | M1 Project setup | Verify clean install, Expo run and baseline build. | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | HIGH | 30 | DONE
P3-02 | Phase 3 – Build (M1–M7) | Day 3–6 | M1 Navigation skeleton | Implement Home/Profile/Edit Profile/Activity/Settings navigation. | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | HIGH | 30 | DONE
P3-03 | Phase 3 – Build (M1–M7) | Day 3–6 | M1 Navigation verification | Navigate every screen and save evidence. | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | HIGH | 30 | DONE
P3-04 | Phase 3 – Build (M1–M7) | Day 3–6 | M2 Base UI structure | Build screen shells and reusable layout patterns. | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | HIGH | 30 | DONE
P3-05 | Phase 3 – Build (M1–M7) | Day 3–6 | M2 Reusable components | Create reusable buttons, inputs, cards/list items. | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | HIGH | 30 | DONE
P3-06 | Phase 3 – Build (M1–M7) | Day 3–6 | M2 Theme implementation | Implement ThemeContext and app-wide theme/preference. | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | HIGH | 30 | DONE
P3-07 | Phase 3 – Build (M1–M7) | Day 3–6 | M2 Theme verification | Verify multiple screens react to theme state. | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | HIGH | 30 | DONE
P3-08 | Phase 3 – Build (M1–M7) | Day 3–6 | M3 Profile model/state | Implement profile state and defaults. | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | HIGH | 30 | DONE
P3-09 | Phase 3 – Build (M1–M7) | Day 3–6 | M3 Profile screen | Render name/avatar/bio from saved/shared data. | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | HIGH | 30 | DONE
P3-10 | Phase 3 – Build (M1–M7) | Day 3–6 | M3 Controlled form | Bind inputs to form state and handle edits. | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | HIGH | 30 | DONE
P3-11 | Phase 3 – Build (M1–M7) | Day 3–6 | M3 Validation | Prevent invalid save and show errors. | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | HIGH | 30 | DONE
P3-12 | Phase 3 – Build (M1–M7) | Day 3–6 | M3 Save/cancel | Save valid data; cancel leaves saved data unchanged. | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | HIGH | 30 | DONE
P3-13 | Phase 3 – Build (M1–M7) | Day 3–6 | M3 Immediate update | Profile updates without restart. | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | HIGH | 30 | DONE
P3-14 | Phase 3 – Build (M1–M7) | Day 3–6 | M4 Activity data | Create activity/interests collection and state. | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | HIGH | 30 | DONE
P3-15 | Phase 3 – Build (M1–M7) | Day 3–6 | M4 FlatList/SectionList | Implement FlatList with keyExtractor, API integration, empty state, search, tags, pagination (SectionList omitted). | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | HIGH | 30 | DONE
P3-16 | Phase 3 – Build (M1–M7) | Day 3–6 | M4 Empty state | Implement safe empty-list UI. | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | HIGH | 30 | DONE
P3-17 | Phase 3 – Build (M1–M7) | Day 3–6 | M4 List interaction | Implement at least one state-changing interaction. | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | HIGH | 30 | DONE
P3-18 | Phase 3 – Build (M1–M7) | Day 3–6 | M5 Storage helper | AsyncStorage calls integrated in ProfileContext and ThemeContext (standalone helper omitted). | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | HIGH | 30 | DONE
P3-19 | Phase 3 – Build (M1–M7) | Day 3–6 | M5 Startup hydration | Read profile/theme/preference at startup. | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | HIGH | 30 | DONE
P3-20 | Phase 3 – Build (M1–M7) | Day 3–6 | M5 Persistence save | Persist profile/theme changes. | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | HIGH | 30 | DONE
P3-21 | Phase 3 – Build (M1–M7) | Day 3–6 | M5 Missing/corrupt fallback | Handle bad local data without crash. | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | HIGH | 30 | DONE
P3-22 | Phase 3 – Build (M1–M7) | Day 3–6 | M5 Restart verification | Restart and verify persisted state. | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | HIGH | 30 | DONE
P3-23 | Phase 3 – Build (M1–M7) | Day 3–6 | M6 Integration | Connect Context, screens, storage and lists end-to-end. | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | MEDIUM | 30 | DONE
P3-24 | Phase 3 – Build (M1–M7) | Day 3–6 | M6 Refactor | Remove duplicated logic and confirm reusable components. | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | MEDIUM | 30 | DONE
P3-25 | Phase 3 – Build (M1–M7) | Day 3–6 | M6 Responsive layout | Check Flexbox/layout on relevant device sizes. | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | MEDIUM | 30 | DONE
P3-26 | Phase 3 – Build (M1–M7) | Day 3–6 | M7 Smoke test | Run complete happy path. | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | MEDIUM | 30 | DONE
P3-27 | Phase 3 – Build (M1–M7) | Day 3–6 | M7 Negative/edge test | Run invalid, empty, missing/corrupt and cancel cases. | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | MEDIUM | 30 | DONE
P3-28 | Phase 3 – Build (M1–M7) | Day 3–6 | M7 Release candidate | Clean run, README updated, no serious runtime errors. | R01–R10; Rubric 3 | Project / Screens / Components / Context / Storage | Design artifacts + code | Working implementation | Git/screenshot/test evidence | Relevant test case | Purpose → input → trigger → transform → output → failure | Code ideas/debug hypotheses | Run and verify independently | MEDIUM | 30 | DONE
P4-01 | Phase 4 – Testing | Day 7 | Populate Test Matrix | Minimum 12 required cases + restart/state/validation/storage/theme/navigation/edge/regression. | Rubric 4 | Test_Matrix | Implemented app | Executable cases with expected results | Test evidence | Run cases | Explain coverage | Edge-case suggestions | Execute manually | HIGH | 45 | DONE
P4-02 | Phase 4 – Testing | Day 7 | Run full test suite | Record actual result, status, bugs, retests and evidence. | Rubric 4 | Test_Matrix | Test cases | Actual results | Screenshots/logs | Retest fixes | Expected vs actual | Missing cases | Run app | HIGH | 45 | DONE
P5-01 | Phase 5 – Debugging | Day 8 | Complete real Debug Log #1 | Symptom → hypothesis → checks → root cause → fix → retest. | Rubric 5 | Debug_Log | Real bug | Complete record | Evidence | Retest/regression | Narrowing strategy | Hypotheses | Verify cause | HIGH | 30 | DONE
P5-02 | Phase 5 – Debugging | Day 8 | Complete real Debug Log #2 | Second real bug with same process. | Rubric 5 | Debug_Log | Real bug | Complete record | Evidence | Retest/regression | Smallest fix | Checklist | Verify fix | HIGH | 30 | DONE
P6-01 | Phase 6 – Interview | Day 9 | Practice core explanations | Navigation, props/state/context, form, Context, list, AsyncStorage, state mutation, structure. | Rubric 6 | Interview_Preparation | Codebase | ≤30 sec answers | Practice notes | Open exact files | Explain without reading | Mock questions | Self-explain | HIGH | 45 | DONE
P6-02 | Phase 6 – Interview | Day 9 | Practice debug explanation | Explain one real bug from symptom to regression. | Rubric 5–6 | Interview_Preparation / Debug_Log | Debug record | Clear explanation | Debug evidence | Regression reasoning | Evidence-based debugging | Follow-ups | Answer from own code | HIGH | 20 | DONE
P7-01 | Phase 7 – Transfer | Day 10 | Complete Basic transfer | Phone/location, reset, filter list or validation change; track impact and retest. | Rubric 7 | Transfer_Practice | Existing app | Implemented + retested | Implemented phone/location fields across ProfileContext, ProfileSchema, ProfileScreen, and EditProfileScreen. | Affected tests | Impact analysis | Affected files/state/tests | Manual retest | HIGH | 45 | DONE
P7-02 | Phase 7 – Transfer | Day 10 | Complete Medium transfer | Favorites persistence, system theme, storage helper or sort/group list. | Rubric 7 | Transfer_Practice | Existing app | Implemented + retested | Before/after | Regression | State/data/storage impact | Impact suggestions | Verify all affected tests | MEDIUM | 60 | IN PROGRESS
P7-03 | Phase 7 – AI | Day 10 | Record AI usage | Log prompt/output/use/change/verification/test/final decision. | Rubric 8 | AI_Usage_Log | AI-assisted work | Traceable evidence | Prompt/output | Verification result | What AI did/did not do | Draft log | Verify actual code/tests | HIGH | 30 | DONE
P7-04 | Phase 7 – Finalization | Day 11 | Complete final checklist | Technical, documentation, interview and demo checks. | Rubric 1–8 | Final_Checklist | All artifacts | No critical gaps | Evidence links | Smoke test | Final evidence | Gap scan | Manual final check | HIGH | 30 | DONE
P7-05 | Phase 7 – Finalization | Day 11 | Run 60-minute pre-assessment | Execute exact 0–10, 10–25, 25–35, 35–45, 45–60 sequence. | Rubric 1–8 | Before_Assessment_60min | Submission | Stable demo readiness | Timing notes | All critical tests | Practice without AI | Simulate mentor questions | Use actual app | HIGH | 60 | DONE
P7-06 | Phase 7 – Finalization | Day 11 | Final clean run + evidence pack | Clean run, README, RTM, DDD, Test Matrix, 2 Debug Logs, AI log if applicable, Git history. | Rubric 1–8 | All sheets/repository | Final source | Submission-ready evidence | Final screenshots/logs | Cold start + demo | Explain every artifact | Final gap scan | Independent verification | HIGH | 60 | DONE

## RTM
Requirement ID | Requirement | Screen | Component | Code/File | Implementation Status | Test Case ID | Evidence | Demo Flow | Interview Topic | Notes
R01 | Project runs in clean environment | App | App root | package.json / README | DONE | TC01 | Clean-run screenshot/log | Cold start | Dependencies + run flow
R02 | Navigation ≥5 screens/areas | All | Navigation | App navigation config | DONE | TC12 | Navigation evidence | Home → Profile → Edit → Activity → Settings | Navigation responsibilities
R03 | Profile displays saved name/avatar/bio | Profile | Profile UI | ProfileScreen | DONE | TC02 | Profile screenshot | Profile read | Props/state/shared profile
R04 | Edit Profile controlled form + validation + save/cancel | Edit Profile | Inputs/Button | EditProfileScreen | DONE | TC03,TC04,TC05 | Validation + save evidence | Profile → Edit → Save/Cancel | Controlled form
R05 | Theme/preference shared with Context | Settings/All | ThemeContext | ThemeContext / Provider | DONE | TC06,TC07 | Theme + restart evidence | Settings → toggle → other screen | Context/rerender
R06 | FlatList + empty state (dummyjson.com API, search, tags, pagination) | Activity | List item | Activity screen | DONE | TC08,TC09,TC10 | List/empty screenshots | Activity → interact | renderItem/keyExtractor | FlatList implemented in ActivityScreen & HomeScreen with API, search, tag filters, pagination, empty state. SectionList omitted.
R07 | AsyncStorage persistence | App/Profile/Settings | ProfileContext / ThemeContext | src/contexts/ProfileContext.js, src/contexts/ThemeContext.js | DONE | TC07,TC11 | Restart evidence | Save → restart | Hydration/serialization | Persisted in ProfileContext (@user_profile) and ThemeContext (@app_theme). Standalone storage helper omitted.
R08 | Reusable components | Multiple | CardItem / CardShortCut | src/components/CardItem.jsx, src/components/CardShortCut.jsx | DONE | TC12 | Component usage | Multiple screens | Reuse/props | CardItem (activity post card) & CardShortCut (navigation shortcut card) used across screens.
R09 | Responsive Flexbox/style | All | Layout | StyleSheet/styles | DONE | TC01,TC16 | Device evidence | Run on emulator/device | Flexbox
R10 | Error/fallback state | Edit/Activity/Startup | Validation/Empty/Fallback | Screens + storage | DONE | TC03,TC09,TC11 | Error/empty/fallback | Invalid/empty/corrupt | Failure path

## Design_Decision_Record
Decision ID | Area | Problem | Chosen Solution | Alternative | Reason | Trade-off | Impact if Requirement Changes | Related Screen | Related Code | Status
D01 | Navigation | Need ≥5 screens/areas | Central navigation configuration | Separate navigation per screen | Central responsibility | Adds route config | New screens modify central map | All | Navigation config | DONE
D02 | State ownership | Local vs shared state | Local UI state; shared profile/theme in Context | Prop drilling | Matches scope | Context rerenders consumers | New shared state may need provider | Profile/Edit/Settings | Context + screens | DONE
D03 | Persistence/hydration | Survive restart + tolerate corrupt data | AsyncStorage calls inside ProfileContext & ThemeContext with startup hydration + safe defaults | Direct storage calls in screens | Centralized handling | Hydration complexity | Storage backend can change behind helper | App/Profile/Settings | src/contexts/ProfileContext.js, src/contexts/ThemeContext.js | DONE
D04 | List structure | Collection + empty state required | FlatList + stable keyExtractor + reusable item | Map rendering | Matches requirement | More setup | Grouping may require SectionList | Activity | Activity + item | DONE
D05 | Reuse | Repeated UI can drift | Shared components with props | Duplicate UI | Consistency + reuse evidence | Generic props need design | New variants may expand API | Multiple | components/ | DONE
D06 | Validation | Invalid data must not persist | Validate before save | Validate after save | Protects persisted state | More form logic | New fields need rules/tests | Edit Profile | EditProfileScreen | DONE

## Test_Matrix
Test ID | Group | Case | Preconditions | Steps | Expected Result | Actual Result | Status | Bug ID | Retest Result | Evidence
TC01 | Startup | First run | Fresh install/no stored data | Launch app | Safe defaults; no crash | Safe default profile (TrangTTT) and theme (light) loaded cleanly on cold start; no crash. | PASSED |  |  | App.js, ProfileContext.js, ThemeContext.js
TC02 | Profile | Profile Read | Profile has saved/default data | Open Profile | Name/avatar/bio render | Profile name, email, bio, and avatar rendered accurately from ProfileContext. | PASSED |  |  | ProfileScreen.jsx
TC03 | Profile | Edit Invalid | Edit open | Enter invalid data → Save | Validation shown; invalid data not persisted | Formik + Yup schema validation blocked save and rendered red error text under invalid fields. | PASSED |  |  | EditProfileScreen.jsx, ProfileSchema.js
TC04 | Profile | Edit Valid | Edit open | Enter valid data → Save | Data saves; Profile updates without restart | Valid inputs updated ProfileContext, saved JSON to AsyncStorage (@user_profile), displayed Toast, and navigated back. | PASSED |  |  | EditProfileScreen.jsx, ProfileContext.js
TC05 | Profile | Edit Cancel | Edit open | Change values → Cancel | Saved profile unchanged | Cancel button called navigation.goBack(); saved profile remained intact without mutation. | PASSED |  |  | EditProfileScreen.jsx
TC06 | Theme | Theme Toggle | Settings available | Toggle theme/preference | App-wide UI updates | Toggling theme in SettingsScreen updated ThemeContext to dark/light, saved preference to AsyncStorage (@app_theme), and re-themed UI. | PASSED |  |  | SettingsScreen.jsx, ThemeContext.js
TC07 | Persistence | Theme/Profile Persistence | Saved state exists | Change → restart → reopen | State survives restart | Saved profile details and active theme preference persisted and hydrated successfully across app restarts. | PASSED |  |  | ProfileContext.js, ThemeContext.js
TC08 | List | List Normal | Activity data exists | Open Activity | Items render with stable keys | FlatList rendered post items fetched from dummyjson.com API with title, body, tags, likes, views using keyExtractor. | PASSED |  |  | ActivityScreen.jsx, activityService.js, CardItem.jsx
TC09 | List | List Empty | Activity data empty | Open Activity | Empty state; no crash | ListEmptyComponent rendered No Activities Found icon and placeholder text when search/filter returned 0 items. | PASSED |  |  | ActivityScreen.jsx
TC10 | List | List Interaction | Activity loaded | Use state-changing interaction | List/UI updates | Toggling Heart icon on post cards dynamically updated local like reaction state and counts in real-time. | PASSED |  |  | CardItem.jsx, ActivityScreen.jsx, HomeScreen.jsx
TC11 | Storage | Storage Corrupt/Missing | Storage missing/malformed | Launch/read state | Fallback/defaults; no crash | Try-catch error handling in ProfileContext and ThemeContext caught corrupted/missing AsyncStorage data and restored safe default state. | PASSED |  |  | ProfileContext.js, ThemeContext.js
TC12 | Navigation | All Screens | App running | Navigate all required areas | All reachable/back works | React Navigation transitioned smoothly across all 5 screens (Home, Activity, Profile, EditProfile, Settings) via Stack and Tab navigators. | PASSED |  |  | AppNavigator.js
TC13 | Regression | State Update | Valid profile saved | Save then revisit screens | State consistent | Saving updated profile updated ProfileScreen and re-populated EditProfileScreen initialValues seamlessly. | PASSED |  |  | ProfileContext.js, EditProfileScreen.jsx
TC14 | Regression | Validation Error Reset | Invalid input attempted | Fix field and retry | Errors clear appropriately | Validation error messages cleared dynamically as soon as valid input was entered into fields. | PASSED |  |  | EditProfileScreen.jsx
TC15 | Regression | Serialization | Stored state exists | Read/write multiple times | Data remains correct | JSON.stringify and JSON.parse preserved object structures cleanly during repeated read/write cycles to AsyncStorage. | PASSED |  |  | ProfileContext.js
TC16 | Edge | Responsive Layout | Relevant emulator/device | Open/resize/rotate if supported | No critical clipping | Flexbox styling with ScrollView, KeyboardAvoidingView, and safe area insets adapted well across screen sizes without clipping. | PASSED |  |  | src/styles/*.jsx
TC17 | Regression | Runtime/Console | Final build | Run core workflow | No serious errors | Full application workflow executed without unhandled exceptions or console errors. | PASSED |  |  | App runtime log

## Interview_Preparation
Question | What I should answer | Code/file to open | ≤30 sec explanation | Practice status
What is a component and why split UI? | Focused UI responsibility; reusable/composable. | Screen + components/ | Purpose → props → state → output → failure. | DONE
How do props, state and Context differ? | Props pass data; state belongs to component; Context shares selected state. | Screen + Context | Who owns data and why. | DONE
Why does changing state rerender? | React updates UI from changed state. | State-owning component | State → render → UI. | DONE
Why not mutate state directly? | Use a new value and setter so React can detect intended update. | List/profile state | Immutable update example. | DONE
Why keyExtractor? | Stable keys let list rendering track items correctly. | Activity | Item → stable key → rendering. | DONE
How does controlled form work? | Input value comes from state; onChange updates state. | EditProfile | Input → state → validate → save. | DONE
How does validation prevent bad persistence? | Validate before save; reject invalid data. | EditProfile | Validate → reject or save. | DONE
Why Context for theme/profile? | Shared across screens and should update consumers. | Contexts | Provider → consumers. | DONE
How does AsyncStorage persistence work? | Serialize on save; deserialize on read; hydrate startup; fallback on failure. | Storage helper/provider | Save → JSON → storage; startup → parse → state. | DONE
What if storage is null/invalid JSON? | Treat as missing/corrupt and use safe defaults. | Storage helper | Read → validate/parse → fallback. | DONE
New screen needs profile data—what changes? | Consume shared Profile Context instead of duplicate state. | New screen + ProfileContext | Existing provider owns profile. | DONE
What is a custom hook? | Reusable stateful logic function when logic repeats or should be separated. | Hook if applicable | Hook logic → component UI. | DONE
Profile not updating after save—how debug? | Trace trigger, form state, validation, shared state, storage, rerender. | Edit/Profile/Context/storage | Symptom → narrow → inspect → fix → retest. | DONE
Adding phone/location—what changes? | Model, form, validation, storage/shared state, UI, tests and evidence as needed. | Profile + Edit + storage + tests | Impact analysis first. | DONE
How did AI help and how verify? | State task, what was used, what changed, and verification. | AI log + changed code | AI suggestion is verified, not blindly accepted. | DONE
Explain one real debug case. | Symptom, expected/actual, hypothesis, checks, root cause, fix, retest. | Debug_Log + code | 30-sec summary then details. | DONE

## Transfer_Practice
Change request | Screen affected | Component affected | State affected | Data affected | Service/storage affected | UI affected | Tests affected | Impact analysis | Implementation | Retest
Basic: Add phone/location | Profile + Edit | Profile/inputs | profile + form | phone/location | AsyncStorage/profile model | Profile + Edit | Read/edit/validation/persistence | Model + validation + storage + UI + tests | Implemented: Added phone & location to ProfileContext, ProfileSchema validation, ProfileScreen UI, and EditProfileScreen inputs. | PASSED: Tested edit, validation, AsyncStorage save, and restart persistence.
Basic: Reset form | Edit Profile | Reset button | form + errors | none | none | Reset controls | Edit invalid/valid/cancel | Clear form/errors without changing saved profile | PLANNED | PLANNED
Basic: Filter activity/interests | Activity | Filter + item | filter + list | filtered collection | none | Filter UI | List normal/empty/interaction | Add filter state and derive visible data | PLANNED | PLANNED
Basic: Change validation rule | Edit Profile | Input/error | form/error | profile field | storage unchanged | Error text | Invalid/valid/cancel | Update rule + tests | PLANNED | PLANNED
Medium: Favorites + persistence | Activity | Favorite control | favorites | favorite IDs | AsyncStorage | Favorite indicator | Interaction + persistence | State + storage + hydration + tests | PLANNED | PLANNED
Medium: System theme | Settings/All | ThemeContext | theme | preference | storage/system | Theme UI | Theme/persistence | Change source of truth while preserving consumers | PLANNED | PLANNED
Medium: Separate storage helper | All persistent | Storage utility | persistence flow | serialized objects | AsyncStorage helper | No direct UI change | Persistence/corrupt | Move storage calls behind helper and retest | PLANNED | PLANNED
Medium: Sort/group list | Activity | List + item | derived list | collection order/groups | none | Headers/order | Normal/empty/interaction | Verify keys and empty state | PLANNED | PLANNED
Advanced: Mock authentication | App/Profile | Auth screens/context | auth | session | mock persistence | Login/logout | Navigation/persistence | Shared auth + protected flow | PLANNED | PLANNED
Advanced: Mock API | Profile/Activity | Service layer | loading/error/data | API-shaped data | mock API | Loading/error UI | Service + edge cases | Add async boundary while preserving UI contract | PLANNED | PLANNED
Advanced: Offline draft | Edit Profile | Draft controls | draft + saved profile | draft data | AsyncStorage | Draft recovery | Form + restart | Separate draft from saved profile | PLANNED | PLANNED

## AI_Usage_Log
ID | Date | Task | Prompt | Purpose | AI Output | What I Used | What I Changed | Verification Method | Test Result | Final Decision
AI-01 | 2026-10-02 | Requirement analysis | Review the Assignment 1 PDF and convert all requirements R01–R10 into a Requirement Traceability Matrix (RTM). For each requirement, identify the expected feature/behavior, the actual file/component in my React Native project that satisfies it, and the minimum test/evidence needed to verify it. Use the assignment PDF as the source of truth and do not invent requirements. | Traceability & completeness check | Structured RTM mapping for R01-R10 | RTM requirement breakdown | Mapped exact codebase file paths (AppNavigator, ProfileContext, etc.) | Compared PDF guide against source code | PASS | Accepted & Verified
AI-02 | 2026-10-02 | Design reasoning | Review my Assignment 1 architecture and help me reason about state ownership and persistence. Analyze which state should be local to a screen/component, which state should be shared through Context, and which state should persist through AsyncStorage. Explain the trade-offs and produce Design Decision Record entries for the chosen navigation, state ownership, persistence/hydration, list structure, and component reuse decisions. | Structure Design Decision Record (DDD) | 6 architectural decision trade-offs (D01-D06) | Core state & persistence trade-offs | Refined D03 to reflect Context-based AsyncStorage persistence | Inspected codebase architecture | PASS | Accepted & Verified
AI-05 | 2026-10-03 | Code explanation | Prepare concise 30-second interview answers for the React Native concepts I need to explain in Assignment 1. Focus on concepts that can be demonstrated directly in my codebase: component/props/state, re-rendering, Context and Provider/Consumer, controlled forms, Formik/Yup validation, navigation, FlatList, renderItem, keyExtractor, state mutation, AsyncStorage persistence/hydration, reusable components, and the Profile/Activity data flow. Anchor each explanation to the actual project instead of giving only textbook definitions. | Interview preparation | Answers for 17 interview questions | Core technical concepts | Anchored explanations to specific codebase file locations | Mock self-interview using codebase | PASS | Accepted & Verified
AI-06 | 2026-10-03 | Transfer practice | Analyze impact and code changes for adding phone/location fields | Implement Basic Transfer task | Impact analysis across model, schema, UI, and storage | Full impact analysis list | Implemented phone & location in ProfileContext, ProfileSchema, ProfileScreen, EditProfileScreen | Tested edit form save and AsyncStorage reload | PASS | Accepted & Verified
AI-07 | 2026-10-03 | Execution flow / Code explanation | Tôi là người mới học React Native và muốn tìm hiểu rõ quy luật thực thi của chương trình theo từng bước (step by step). Hãy phân tích quy luật thực thi của ứng dụng trong Assignment 1 và hiển thị workflow thực thi dưới dạng: method() → method() → method() → .... Bắt đầu từ khi tôi chạy npm start, cho đến khi ứng dụng nạp dữ liệu và hiển thị dữ liệu lên List. Hãy giải thích chi tiết từng bước và từng dòng lệnh quan trọng để giúp tôi hiểu được quá trình thực thi thực tế của chương trình. Lưu ý quan trọng: Mọi phân tích phải bắt đầu từ App.js trước, sau đó đi từ từ xuống các component, navigator, screen, context, service, storage/helper... theo đúng luồng thực thi thực tế của project. Không được nhảy thẳng vào một file hoặc method ở giữa. Hãy chỉ ra rõ: File nào được chạy trước. Method/function nào được gọi. Method nào gọi method nào. Dữ liệu được lấy từ đâu. Dữ liệu đi qua những file/function nào. Cuối cùng dữ liệu được đưa vào List và render lên UI như thế nào. Mục tiêu: Tôi muốn hiểu được toàn bộ execution flow của ứng dụng từ lúc npm start → App.js → các thành phần bên dưới → lấy dữ liệu → xử lý dữ liệu → render dữ liệu lên List, thay vì chỉ biết từng file riêng lẻ làm gì. | Understand the actual runtime and data-execution flow instead of memorizing individual files | Step-by-step flow from npm start → Expo/Metro → index.js → App() → providers → navigation → screen → useEffect() → service → Axios → API → state → FlatList → renderItem() → reusable card → UI | Used the flow to prepare code explanation/demo and connect individual files into one execution chain | Traced the actual project source from entry point through App, navigation, contexts, screens, service and FlatList; compared expected flow with runtime behavior | PASS | Accepted & Verified
AI-08 | 2026-10-06 | Professional engineering / List design | Continue: I want to understand professional problems and engineering practices used by large software companies, professional software projects, and production e-commerce projects. Please explain the design and use of ListView/list components in a real e-commerce project, specifically how they are applied and used in production. Relate the explanation to React Native FlatList and the current Assignment 1 implementation. | Understand how the current academic FlatList implementation relates to production-scale list design | Explained list responsibilities such as data source, item rendering, keys, pagination/infinite loading, refresh, loading/empty/error states, performance, state ownership and reusable item components; connected concepts to e-commerce catalog/product-list scenarios | Professional list-design concepts that can be applied when explaining the current FlatList implementation | No unnecessary production features were added to Assignment 1; used the concepts mainly for understanding, code explanation and future design reasoning | Compared professional concepts against current HomeScreen/ActivityScreen, FlatList, CardItem, API service, search/filter and pagination implementation; checked against Assignment 1 list requirements | PASS | Accepted for learning/design reasoning; no unnecessary code change
AI-09 | 2026-10-03 / 2026-10-05 | Documentation / README | Review and structure an English README for MMA301 Assignment 1 covering features, architecture, navigation, state ownership, AsyncStorage, Formik/Yup, Axios/DummyJSON, FlatList, requirements and limitations | Produce submission-ready project documentation | README structure and concise descriptions of architecture, features, persistence, API/list behavior and limitations | Documentation structure and technical descriptions | Adapted the README to the actual project rather than copying generic architecture; added actual project features and implementation details | Compared README statements with source code and assignment requirements | PASS | Accepted & Verified
AI-10 | 2026-10-02 → 2026-10-05 | Runtime debugging / troubleshooting | Analyze React Native runtime/import/state issues encountered during Assignment 1, including component import/export problems, profile data/state issues and development-environment problems | Diagnose actual runtime/build issues without blindly changing unrelated code | Root-cause hypotheses and targeted fixes for issues such as CardShortCut import/export, profile.name null handling, and Windows case-only file rename behavior | Applied only fixes that matched the actual source/error and project structure | Re-ran the affected screen/workflow and checked imports/state behavior after each fix | PASS | Accepted & Verified
AI-11 | 2026-10-05 → 2026-10-06 | Final verification / engineering practice | Review the Assignment 1 finalization process from testing, debugging and verification through README, Test Matrix, Debug Logs, AI Usage Log and final demo preparation | Ensure the submission evidence is complete and consistent with the assignment guide | Final verification checklist and recommended relationship between test evidence, debug logs, AI log, README and Git history | Used the checklist to organize final evidence instead of changing working features unnecessarily | Cross-checked submission artifacts against Assignment 1 requirements and actual project state | PASS* | Accepted; final evidence must reflect actual executed tests

## Final_Checklist
Section | Checklist Item | Checkbox | Status | Evidence | Notes
Technical | App runs clean | ☑ | DONE | App.js, package.json
Technical | ≥5 screens/areas | ☑ | DONE | AppNavigator.js (5 screens)
Technical | Navigation verified | ☑ | DONE | AppNavigator.js
Technical | Profile read works | ☑ | DONE | ProfileScreen.jsx
Technical | Edit form works | ☑ | DONE | EditProfileScreen.jsx
Technical | Validation blocks invalid save | ☑ | DONE | ProfileSchema.js, EditProfileScreen.jsx
Technical | Cancel preserves saved data | ☑ | DONE | EditProfileScreen.jsx
Technical | Theme/preference app-wide | ☑ | DONE | ThemeContext.js, SettingsScreen.jsx
Technical | FlatList/SectionList | ☑ | DONE | ActivityScreen.jsx, HomeScreen.jsx
Technical | Empty state | ☑ | DONE | ActivityScreen.jsx (ListEmptyComponent)
Technical | AsyncStorage persistence | ☑ | DONE | ProfileContext.js, ThemeContext.js
Technical | Restart persistence | ☑ | DONE | ProfileContext.js, ThemeContext.js
Technical | Missing/corrupt fallback | ☑ | DONE | ProfileContext.js, ThemeContext.js
Technical | Responsive layout | ☑ | DONE | src/styles/*.jsx
Technical | Reusable components | ☑ | DONE | CardItem.jsx, CardShortCut.jsx
Technical | No serious runtime/console errors | ☑ | DONE | App runtime log
Documentation | README complete | ☑ | DONE | README.md
Documentation | RTM complete | ☑ | DONE | RTM sheet
Documentation | DDD complete | ☑ | DONE | Design_Decision_Record sheet
Documentation | Test Matrix actual results | ☑ | DONE | Test_Matrix sheet
Documentation | 2 real Debug Logs | ☑ | DONE | Plan / Debug logs
Documentation | AI Log if applicable | ☑ | DONE | AI_Usage_Log sheet
Documentation | Git history if required | ☑ | DONE | Git repository
Interview | Edit flow explanation | ☑ | DONE | EditProfileScreen.jsx, ProfileContext.js
Interview | Theme/persistence explanation | ☑ | DONE | ThemeContext.js, AsyncStorage
Interview | State ownership explanation | ☑ | DONE | ProfileContext.js, ThemeContext.js
Interview | Navigation explanation | ☑ | DONE | AppNavigator.js
Interview | List/key/empty explanation | ☑ | DONE | ActivityScreen.jsx (FlatList)
Interview | AsyncStorage hydration/fallback | ☑ | DONE | ProfileContext.js, ThemeContext.js
Interview | Real debug explanation | ☑ | DONE | Plan & Debug logs
Interview | Transfer explanation | ☑ | DONE | Transfer_Practice sheet
Interview | AI verification explanation | ☑ | DONE | AI_Usage_Log sheet
Final Demo | Cold start works | ☑ | DONE | App.js
Final Demo | Main workflow works | ☑ | DONE | MainTabs & Stack screens
Final Demo | Negative/edge demo ready | ☑ | DONE | Test_Matrix edge cases
Final Demo | Debug explanation ready | ☑ | DONE | Debug logs
Final Demo | Modification explanation ready | ☑ | DONE | Transfer_Practice sheet
Final Demo | Evidence easy to locate | ☑ | DONE | Workbook & source repo

## Overview
Metric | Value | Notes
Total Tasks | 74 | Main plan | CÁCH DÙNG FILE
TODO | 0 | Not started | ① Làm theo MMA301_Assignment1_Plan. ② Cập nhật Status + Evidence sau mỗi task. ③ Test thật thì điền Actual Result + Status. ④ Interview: luyện trả lời bằng chính code của mình. ⑤ Transfer: ghi impact → implementation → retest.
DOING | 0 | In progress
DONE | 73 | Completed
BLOCKED | 0 | Blocked
Progress % | 98.65% | DONE / total
HIGH Priority | 55 | High priority
MEDIUM Priority | 7 | Medium priority
LOW Priority | 0 | Low priority
RTM Requirements | 10 | R01–R10
Rubric Areas | 10 | Rubric 1–8
Test Cases | 17 | Required + extra
Debug Logs | 2 | Practice + real placeholders
Transfer Tasks | 11 | Basic/Medium/Advanced
Tasks by Phase
Phase 1 – Requirement Analysis | 22 | Main plan task count
Phase 2 – Design | 12 | Main plan task count
Phase 3 – Build (M1–M7) | 28 | Main plan task count
Phase 4 – Testing | 2 | Main plan task count
Phase 5 – Debugging | 2 | Main plan task count
Phase 6 – Interview | 2 | Main plan task count
Phase 7 – Transfer | 2 | Main plan task count
Evidence gaps to watch
Actual Test Results | 17 | Fill after executing tests
Real Debug Logs | 2 | Replace placeholders with real root causes
Final Checklist DONE | 38 | Complete before submission
Interview DONE | 16 | Practice without reading